TIME AND MATERIALS CONSTRUCTION AGREEMENT

Authorization to Proceed Without a Fixed Contract Sum

MC-OWN-TM-001  |  REV. 1.2

| AGREEMENT INFORMATION | AGREED VALUE |
| --- | --- |
| Agreement date |  |
| Owner legal name and legal status |  |
| Owner address, representative, and contact |  |
| Project name and address |  |
| Initial Work description |  |
| Contractor | Mefford Contracting, LLC ¦ 1585 Mercer Road, Suite 110, Lexington, Kentucky 40511 |

| OWNER'S T&M AUTHORIZATION | APPROVED RATE / TERM |
| --- | --- |
| Contractor Fee / Profit Percentage | % ____________ |
| Initial deposit or advance payment | $____________ |
| Invoice frequency and payment due date | Monthly invoices; payment due 15 calendar days after receipt |
| Work commencement / Notice to Proceed |  |
| Fixed total Contract Sum or maximum price | None unless established by a later written Modification signed by Owner and Contractor |

# TABLE OF ARTICLES

| 1 | AGREEMENT AND GENERAL PROVISIONS |
| --- | --- |
| 2 | AUTHORIZATION TO PROCEED AND SCOPE OF WORK |
| 3 | TIME-AND-MATERIALS COMPENSATION |
| 4 | COST RECORDS, TICKETS, AND INVOICING |
| 5 | CONTRACT TIME, SCHEDULE, AND DELAY |
| 6 | DESIGN INFORMATION AND PROFESSIONAL SERVICES |
| 7 | CONTRACTOR'S RESPONSIBILITIES |
| 8 | CONSTRUCTION REQUIREMENTS |
| 9 | CHANGES AND ADDITIONAL WORK |
| 10 | OWNER'S RESPONSIBILITIES |
| 11 | PAYMENTS AND PROJECT COMPLETION |
| 12 | PROTECTION, INSURANCE, BONDS, AND INDEMNITY |
| 13 | CORRECTION AND WARRANTY |
| 14 | SUSPENSION AND TERMINATION |
| 15 | CLAIMS, DISPUTES, AND MISCELLANEOUS PROVISIONS |
| 16 | CONTRACT DOCUMENTS AND EXECUTION |

By executing this Agreement, Owner authorizes Contractor to proceed before a total Project budget or final price is established. Owner shall pay labor at the agreed billing rates, reimbursable T&M Cost, any expressly stated item-specific markups, and the Contractor Fee / Profit Percentage calculated under Article 3. Cost-to-date reports, funding information, anticipated commitments, and planning estimates are not a maximum price, warranty, or prediction of final cost unless both parties sign a Modification that expressly creates a not-to-exceed amount.

# ARTICLE 1  |  AGREEMENT AND GENERAL PROVISIONS

1.1  Time-and-Materials Engagement.  Owner engages Contractor to furnish the supervision, labor, materials, equipment, temporary facilities, procurement, coordination, construction, testing support, commissioning support, and closeout included in the Work. Compensation is determined under Article 3 rather than by a fixed total price.

1.2  Contract Documents.  The Contract Documents consist of this Agreement, specifically listed Work authorizations, drawings, specifications, reports, attachments, approved Modifications, written directives issued under Article 9, and other documents expressly incorporated by a writing signed by both parties. They form the entire agreement and supersede prior negotiations and representations concerning the same Work.

1.3  Definitions.  Work means the construction and related services authorized under this Agreement. Project means the total undertaking of which the Work may be all or a part. T&M Cost means labor charges at the stated billing rates and the reimbursable material, equipment, subcontractor, consultant, permit, freight, tax, and other direct costs described in Article 3, before any Item-Specific Markup or Contractor Fee / Profit. Actual Net Cost means the amount actually paid or payable after ordinary trade discounts, rebates, refunds, and credits, plus Project-specific tax, freight, delivery, storage, and handling permitted by Article 3. Item-Specific Markup means only the percentage, if any, entered for a listed cost category. Contractor Fee / Profit means the overall percentage stated in Article 3 and applied once to T&M Cost. Neither an Item-Specific Markup nor Contractor Fee / Profit is applied to the other unless a signed Work Authorization expressly states otherwise. Modification means a written amendment, Change Order, or Work Authorization signed by both parties. Day means calendar day unless expressly stated otherwise.

1.4  Project Team.  Each party shall act through its authorized representative. A representative may bind the appointing party only within the authority stated in this Agreement or separately confirmed in writing.

| PROJECT TEAM | NAME / CONTACT / ROLE |
| --- | --- |
| Owner representative and contact |  |
| Owner architect / engineer or consultant |  |
| Contractor representative and contact |  |
| Other Owner reviewers or separate contractors |  |

1.5  Binding Dispute Resolution.  Claims not resolved by project-level discussion, executive negotiation, and mediation shall be resolved by the method selected below. If neither method is selected, litigation in a court of competent jurisdiction shall apply.

| DISPUTE ELECTION | AGREED TERM |
| --- | --- |
| Binding method |  |
| Mediation provider, venue, or arbitration rules |  |

1.6  No Third-Party Beneficiary.  The Contract creates rights only between Owner and Contractor. Architects, engineers, consultants, subcontractors, suppliers, lenders, tenants, and separate contractors are not third-party beneficiaries unless a signed provision expressly states otherwise.

# ARTICLE 2  |  AUTHORIZATION TO PROCEED AND SCOPE OF WORK

2.1  Immediate Authorization.  Owner authorizes Contractor to mobilize, procure, coordinate, and perform the Work described below beginning on the stated commencement date. Contractor may perform reasonably necessary planning, supervision, purchasing, scheduling, site setup, protection, and closeout associated with the authorized Work and bill that effort under Article 3.

| AUTHORIZED WORK | SCOPE / RESPONSIBILITY |
| --- | --- |
| Initial authorized Work |  |
| Initial priorities or sequence |  |
| Known exclusions and work by others |  |
| Owner-furnished materials, equipment, information, or access |  |
| Required permits, testing, training, and closeout |  |

2.2  No Fixed Total Price.  This Agreement does not establish a fixed Contract Sum, guaranteed total, or maximum price. Owner is responsible for all properly incurred T&M Cost and Contractor Fee / Profit through the effective date of any written stop direction, suspension, termination, or signed limit, together with authorized demobilization, cancellation, restocking, protection, and closeout cost.

2.3  Cost Information; No Final-Cost Warranty.  Contractor shall report cost incurred, outstanding commitments, and known near-term funding needs as the Work develops. Because the engagement is open-ended T&M, Contractor is not required to predict the total final Project cost or the cost of remaining Work. Any planning estimate or funding request is based on information then available and is not a promise, warranty, fixed price, or cost cap. A variance does not reduce amounts otherwise due.

2.4  Later Limits.  A not-to-exceed amount or other cost limit is effective only when a writing signed by Owner and Contractor identifies the exact Work covered, exclusions, rate and markup assumptions, contingency treatment, effective date, and consequences of reaching the limit. Contractor shall notify Owner when it reasonably expects to reach an effective limit and may stop affected Work unless the parties authorize additional compensation, except for emergency protection.

2.5  Work Authorizations.  The parties may issue additional Work authorizations under this Agreement. Each authorization may describe scope, priority, location, responsible participants, schedule, special rates, and reporting requirements. An authorization need not state a total price unless the parties intend to create a separate written limit.

| Work authorization | Description / location | Requested start | Owner authorization |
| --- | --- | --- | --- |

# ARTICLE 3  |  TIME-AND-MATERIALS COMPENSATION

3.1  Compensation Formula.  Owner shall pay the sum of: labor at the agreed hourly billing rates; actual material, equipment, subcontractor, consultant, permit, freight, tax, and other reimbursable cost; the item-specific markups stated below; and the Contractor Fee / Profit Percentage applied once to the stated fee basis. No fee is applied to another fee or markup unless expressly stated.

3.2  Hourly Labor Billing Rates.  The following are billing rates for time reasonably devoted to the Work, including authorized project management, supervision, estimating, procurement, scheduling, meetings, coordination, field labor, administration, mobilization, travel, setup, protection, cleanup, and closeout. Premium rates apply as stated below.

| Labor classification | Straight time / hr | Overtime / hr | Double time / hr | Notes |
| --- | --- | --- | --- | --- |
| Project executive | $____________ | $____________ | $____________ |  |
| Project manager | $____________ | $____________ | $____________ |  |
| Assistant project manager / project engineer | $____________ | $____________ | $____________ |  |
| Superintendent | $____________ | $____________ | $____________ |  |
| Assistant superintendent | $____________ | $____________ | $____________ |  |
| Estimator / preconstruction | $____________ | $____________ | $____________ |  |
| Safety / quality personnel | $____________ | $____________ | $____________ |  |
| Foreman | $____________ | $____________ | $____________ |  |
| Carpenter / skilled trade | $____________ | $____________ | $____________ |  |
| Laborer | $____________ | $____________ | $____________ |  |
| Equipment operator | $____________ | $____________ | $____________ |  |
| Administrative / accounting | $____________ | $____________ | $____________ |  |
| Other | $____________ | $____________ | $____________ |  |

| LABOR RATE RULES | AGREED TERM |
| --- | --- |
| Rate effective date and adjustment date |  |
| Minimum call-out or minimum daily hours |  |
| Travel, mobilization, per diem, and mileage treatment |  |
| Shift differential, weekend, holiday, or emergency premium |  |
| Labor rate components included in stated billing rates |  |

3.3  Overtime and Premium Time.  Contractor shall obtain advance approval for avoidable premium time when practicable. Advance approval is not required for emergency protection, Owner-requested acceleration, schedule recovery from Owner-caused delay, or Work that must continue to avoid damage or material disruption. The stated premium rates apply to qualifying hours.

3.4  Materials and Consumables.  Materials and consumables are billed at Contractor's actual net purchase cost after ordinary trade discounts, plus freight, delivery, sales or use tax, storage, handling, and the applicable markup below. Credits actually received for returned material are passed through after restocking, return freight, handling, and related cost.

3.5  Equipment.  Owned equipment is billed at the agreed hourly, daily, weekly, or monthly rates for time assigned to the Work, including reasonable standby when the equipment cannot be economically released. Rented equipment is billed at actual rental and related cost plus the stated markup. Operating labor is billed separately unless the equipment rate expressly includes it.

| Owned equipment | Unit / size | Hourly | Daily | Weekly | Included cost / standby rule |
| --- | --- | --- | --- | --- | --- |
|  |  | $______ | $______ | $______ |  |
|  |  | $______ | $______ | $______ |  |
|  |  | $______ | $______ | $______ |  |
|  |  | $______ | $______ | $______ |  |
|  |  | $______ | $______ | $______ |  |
|  |  | $______ | $______ | $______ |  |
|  |  | $______ | $______ | $______ |  |
|  |  | $______ | $______ | $______ |  |

3.6  Subcontractors, Consultants, and Other Direct Cost.  Subcontractors, lower-tier suppliers, consultants, professional services, permits, testing, bonds, insurance specifically attributable to the Work, temporary utilities, freight, delivery, disposal, travel, lodging, reproduction, technology, and other authorized direct cost are reimbursable at actual cost plus the applicable markup and Contractor Fee / Profit treatment stated below.

| Cost category | Cost basis | Item-specific markup | Contractor Fee / Profit treatment |
| --- | --- | --- | --- |
| Labor billing rates | Rates in Article 3.2 | Included in stated rates | Fee applies to base T&M Cost |
| Materials and consumables | Actual net cost | % ____________ | Fee applies to base T&M Cost |
| Owned equipment | Listed rates | Included in listed rates | Fee applies to base T&M Cost |
| Rented equipment | Actual cost | % ____________ | Fee applies to base T&M Cost |
| Subcontractors and suppliers | Actual cost | % ____________ | Fee applies to base T&M Cost |
| Consultants / professional services | Actual cost | % ____________ | Fee applies to base T&M Cost |
| Permits, testing, fees, freight, and other direct cost | Actual cost | % ____________ | Fee applies to base T&M Cost |
| Insurance and bond cost specifically required for Work | Actual cost | % ____________ | Fee applies to base T&M Cost |

| FEE, PROFIT, AND MARKUP RULES | AGREED TERM |
| --- | --- |
| Contractor Fee / Profit Percentage | % ____________ |
| Fee / Profit cost categories and calculation basis | Applied once to all T&M Cost before Item-Specific Markup; no compounding |
| General overhead or project general conditions not included in rates | Project-specific general conditions are billable at stated rates or Actual Net Cost; home-office overhead is included in Fee / Profit unless expressly stated |
| Small tools, vehicles, technology, and consumables treatment | Actual Project cost or stated rate; Fee / Profit applies |
| Sales tax or other tax treatment | Actual Project cost when applicable; Fee / Profit applies |

3.7  Rate Changes.  Rates and percentages remain in effect through the stated adjustment date. Contractor may thereafter adjust rates for documented wage, benefit, insurance, tax, fuel, market, or collective-bargaining changes upon reasonable written notice. A special rate agreed for a Work authorization controls only for that authorization.

# ARTICLE 4  |  COST RECORDS, TICKETS, AND INVOICING

4.1  Daily Records.  Contractor shall maintain reasonably detailed records of labor classifications and hours, equipment use, material deliveries, subcontractor activity, and significant Work performed. Records may be electronic and may be organized by day, Work authorization, area, or cost code.

4.2  T&M Tickets and Weekly Reconciliation.  Contractor shall submit daily or periodic T&M tickets and, once each week, a summary of the preceding week's labor, equipment, materials, subcontractors, authorized markups, and cumulative T&M Cost. Owner shall identify any specific disputed entry and its basis in writing within three business days after receiving the weekly summary, and the parties shall promptly reconcile the identified item. Amounts not specifically disputed may be included in the next invoice. A signature acknowledges receipt and observed activity; it does not create a fixed price or waive correction of a documented error. Failure or refusal to sign does not bar payment when Contractor provides other reasonable Project support.

| T&M RECORDS | AGREED REQUIREMENT |
| --- | --- |
| Required ticket frequency and format | Daily tickets; weekly cost reconciliation |
| Owner representative authorized to acknowledge tickets |  |
| Cost codes, locations, or Work authorization breakdown |  |
| Special supporting documentation | Project-specific support for billed actual-cost items; no enterprise-wide records |

4.3  Invoices.  Contractor shall invoice at the agreed frequency. Each invoice shall show the billing period, labor by classification and hours, equipment, materials, subcontractors, other reimbursable cost, applicable markups, Contractor Fee / Profit, previous payments, credits, retainage if any, and amount due.

| INVOICE AND PAYMENT TIMING | AGREED TERM |
| --- | --- |
| Invoice frequency and cutoff | Weekly reconciliation; invoices monthly |
| Invoice delivery method / recipient |  |
| Owner review period | 7 calendar days; written line-item dispute required |
| Payment due after receipt | 15 calendar days |
| Late-payment interest | 12% per annum or the maximum lawful rate, whichever is less |

4.4  Project-Specific Cost Support and Audit.  Contractor shall provide time records, supplier invoices, equipment records, subcontractor invoices, and other reasonable support for actual-cost items billed to this Project. Any audit is limited to the identified Project invoice, Work Authorization, cost code, and cost category in dispute; it does not create a general right to inspect Contractor's other projects, enterprise records, agreed billing-rate composition, or unrelated confidential information. Owner may review the relevant Project records during the Work and for the period stated below on at least five business days' notice and without unreasonably disrupting operations.

| PROJECT-SPECIFIC COST RECORDS | AGREED TERM |
| --- | --- |
| Audit scope and request period | This Project's billed actual-cost items only; during Work and 12 months after Final Payment |
| Record retention period | 2 years after Final Payment |
| Electronic platform or cost-report format |  |

4.5  Cost-to-Date Reporting and Notice.  Contractor shall periodically report T&M Cost incurred, known commitments, and a material scope, schedule, procurement, condition, or price development. A statement of anticipated near-term expenditures is solely for cash-flow coordination and does not create a final-cost warranty, cost cap, or transfer to Contractor the risk of authorized T&M Cost.

# ARTICLE 5  |  CONTRACT TIME, SCHEDULE, AND DELAY

5.1  Schedule.  Contractor shall prepare and update a practical schedule showing authorized Work, decisions, procurement, construction, occupancy, Substantial Completion, and Final Completion to the extent the evolving scope permits. Dates are planning targets unless expressly identified as contractual milestones below.

| PROJECT SCHEDULE | DATE / PERIOD |
| --- | --- |
| Conditions before commencement |  |
| Work commencement / Notice to Proceed |  |
| Target Substantial Completion |  |
| Target Final Completion |  |
| Owner occupancy or phased completion |  |

| Contractual milestone, if any | Responsible party | Required date | Consequence / notes |
| --- | --- | --- | --- |

5.2  Excusable and Compensable Delay.  Contractor is entitled to a reasonable extension for delay beyond its reasonable control, including Owner or design-professional acts or omissions, changed or added Work, late decisions or information, differing conditions, transportation interruption, abnormal weather, epidemic, governmental action, utility delay, casualty, and force majeure. Because the Work is T&M, Contractor is also entitled to compensation at the agreed rates for standby, protection, escalation, remobilization, extended supervision, and other reasonable delay cost not caused by Contractor's breach.

5.3  Delay Notice and Mitigation.  Contractor shall provide reasonably prompt notice of a known material delay, update schedule effects as they develop, and use reasonable efforts to mitigate. Late notice reduces recovery only to the extent Owner is materially prejudiced, unless mandatory law requires otherwise.

| PROJECT DELAY TERMS | AGREED TERM |
| --- | --- |
| Delay notice period |  |
| Special acceleration or premium-time approval rule |  |
| Liquidated damages, only if expressly agreed |  |

# ARTICLE 6  |  DESIGN INFORMATION AND PROFESSIONAL SERVICES

6.1  Design Responsibility.  Contractor is not the Project's architect or engineer and does not assume responsibility for the adequacy, completeness, code compliance, or coordination of Owner-provided design. Contractor shall report a recognized error, omission, conflict, ambiguity, or code concern and shall not knowingly proceed with affected Work until clarification is received, except in an emergency.

6.2  Owner-Provided Information.  Owner shall timely furnish drawings, specifications, surveys, reports, existing-condition information, selections, and decisions needed for the Work. Contractor may rely on their accuracy and completeness except for deficiencies reasonably recognizable by a qualified contractor. Cost and delay from omitted, revised, late, or inaccurate information are compensable T&M Cost.

6.3  Included Professional or Delegated Design.  Professional services or delegated design are included only to the extent specifically identified below. Such services shall be performed by properly licensed professionals and are governed by the ordinary professional standard of care. Consultant cost and Contractor's related coordination are compensated under Article 3.

| Professional / delegated-design service | Scope / performance criteria | Responsible party | Rate / cost treatment |
| --- | --- | --- | --- |

6.4  Submittals and Requests for Information.  Contractor shall review and coordinate shop drawings, product data, samples, and delegated-design submittals before required Owner or design-professional review. Responses that add or change Work are compensated under this Agreement. Review does not transfer responsibility for construction means, methods, safety, coordination, or expressly delegated design.

| DESIGN AND SUBMITTAL ADMINISTRATION | AGREED TERM |
| --- | --- |
| Owner design professional and contact |  |
| Required submittals or approvals |  |
| Owner / design-professional review period |  |
| Digital data or model-use requirements |  |

# ARTICLE 7  |  CONTRACTOR'S RESPONSIBILITIES

7.1  Licensing and Performance.  Contractor shall maintain required licenses and shall perform the Work through qualified employees, subcontractors, suppliers, and any delegated-design professionals. Contractor is responsible to Owner for their acts and omissions within the Work.

7.2  Supervision and Construction Means.  Contractor shall supervise and direct the Work and is solely responsible for construction means, methods, techniques, sequences, procedures, coordination, and site safety, except for a method expressly required by Owner over Contractor's written objection.

7.3  Schedules, Meetings, and Reports.  Contractor shall conduct the meetings reasonably required by the Project and keep Owner informed of progress, quality, decisions, schedule, procurement, safety, T&M Cost incurred, known commitments, and material risks.

7.4  Key Participants.  Contractor shall assign the following key participants. Substitution requires reasonable prior notice and a replacement with comparable qualifications. A blank line does not restrict Contractor's ordinary procurement authority.

| Role / trade | Name | Company | Contact / included scope |
| --- | --- | --- | --- |
| Project executive |  | Mefford Contracting, LLC |  |
| Project manager |  | Mefford Contracting, LLC |  |
| Superintendent |  | Mefford Contracting, LLC |  |
| Foreman |  |  |  |
| Major subcontractor |  |  |  |
| Delegated-design professional |  |  |  |
| Other key participant |  |  |  |

7.5  Labor, Materials, and Lower Tiers.  Contractor shall furnish the labor, materials, equipment, temporary facilities, supervision, and services reasonably required for authorized Work and shall timely pay lower tiers from payments received for their Work. Materials and equipment shall be new unless otherwise permitted, of good quality, and free from material defects not inherent in the specified quality.

7.6  Taxes, Permits, and Fees.  Responsibility for taxes, permits, licenses, inspections, utility charges, and similar items is stated in Articles 2, 3, and 8. New or changed governmental requirements are compensable T&M Cost unless caused by Contractor's noncompliance.

7.7  Contingent Assignment.  Contractor's subcontracts are conditionally assigned to Owner, effective only if Owner terminates Contractor for cause, accepts the assignment in writing, and assumes Contractor's obligations arising after acceptance.

7.8  Independent Contractor.  Contractor is an independent contractor. The parties' cooperation and Contractor's management of the Work do not create a partnership, joint venture, fiduciary duty, or employment relationship.

# ARTICLE 8  |  CONSTRUCTION REQUIREMENTS

8.1  Commencement and Site Control.  Contractor shall begin after the commencement conditions are satisfied and shall control its construction operations within the site limits, access rules, working hours, and occupied-facility restrictions stated below or in an authorized Work document.

| SITE REQUIREMENTS | AGREED TERM |
| --- | --- |
| Site access, working hours, and security |  |
| Occupied-area, shutdown, or operational restrictions |  |
| Temporary utilities, facilities, and storage |  |
| Owner safety or site-specific requirements |  |

8.2  Substitutions and Selections.  Contractor shall identify material substitutions affecting appearance, performance, maintenance, warranty, or code compliance and obtain required Owner or design-professional approval. Time spent and cost incurred evaluating, pricing, procuring, and coordinating substitutions or Owner selections are compensable under Article 3.

8.3  Concealed or Unknown Conditions.  If concealed or unknown physical conditions materially differ from disclosed information or ordinary conditions for comparable work, Contractor shall protect the area and give prompt notice before disturbance when practicable. Investigation, protection, redesign, changed Work, delay, and resulting cost are compensable under this Agreement unless caused by Contractor's breach.

8.4  Hazardous and Regulated Conditions.  Unless expressly included, Contractor is not responsible for testing, design, removal, transport, or remediation of preexisting hazardous materials, human remains, archaeological materials, wetlands, endangered species, or other regulated conditions. Contractor shall stop affected Work, secure the area, and notify Owner. Owner shall obtain required professional and governmental direction.

8.5  Site Documents, Access, and Use.  Contractor shall maintain current Work documents, approved submittals, authorizations, reports, and available records at the site or in the agreed electronic system. Owner and its consultants may access the Work on reasonable notice without interfering with operations or assuming responsibility for safety or means and methods.

8.6  Cutting, Patching, and Cleanup.  Contractor shall perform cutting and patching required for authorized Work, protect adjacent property, and keep the site reasonably free of waste. Cost and delay caused by Owner's forces, occupants, or separate contractors are compensable under Article 3.

8.7  Owner and Separate Contractors.  Owner may perform work with its own forces or separate contractors. Owner shall coordinate them with Contractor's schedule, require compliance with site safety and insurance requirements, and bear cost or delay caused by late, defective, or interfering separate work.

8.8  Permits, Testing, Commissioning, and Closeout.  Responsibility for permits, inspections, testing, commissioning, training, regulatory completion, and closeout is allocated below. Contractor-performed or Contractor-procured items are compensated under Article 3.

| Item | Responsible party | Scope / cost treatment / notes |
| --- | --- | --- |
| Zoning, land use, and entitlements |  |  |
| Building and trade permits |  |  |
| Survey and construction layout |  |  |
| Geotechnical and environmental services |  |  |
| Special inspections and testing laboratory |  |  |
| Commissioning and training |  |  |
| Certificate of occupancy and closeout |  |  |

# ARTICLE 9  |  CHANGES AND ADDITIONAL WORK

9.1  Changes Within T&M Structure.  Owner may add, delete, revise, resequence, accelerate, suspend, or otherwise change authorized Work by written amendment, Work authorization, Change Order, or written directive. Unless a signed writing states a different price method, changed Work remains compensable under the rates, costs, markups, and Contractor Fee / Profit in Article 3.

9.2  Written Directives.  Owner may direct Work before all scope details are complete. Contractor shall proceed only to the extent lawful and safe, maintain contemporaneous records, and report known material cost or schedule effects. Undisputed amounts remain payable in ordinary invoices.

9.3  Owner and Field Directions.  Contractor may rely on written directions from Owner's authorized representative. A direction from another person is not binding unless confirmed by an authorized representative, except Contractor may act in an emergency to protect persons or property.

9.4  Deleted or Stopped Work.  Owner may direct Contractor to stop or delete future Work. Owner remains responsible for labor and cost incurred or reasonably committed before the effective direction, together with cancellation, restocking, return freight, protection, demobilization, and applicable Fee / Profit. Actual credits received are passed through under Article 3.

9.5  No Oral Modification of Commercial Terms.  A meeting comment, site conversation, ticket signature, submittal response, schedule update, payment, or failure to object does not alter the rates, markups, fee, payment terms, or other commercial provisions unless confirmed in an authorized writing.

# ARTICLE 10  |  OWNER'S RESPONSIBILITIES

10.1  Representative and Decisions.  Owner shall designate a representative with authority to act for Owner and shall render decisions, approvals, selections, and consolidated comments with reasonable promptness in accordance with the evolving schedule.

10.2  Information and Services.  Owner shall timely furnish accurate program information, drawings, specifications, surveys, legal descriptions, title information, easements, existing-condition records, hazardous-material information, geotechnical and environmental reports, utility information, and other services assigned to Owner. Contractor may rely on such information subject to Article 6.

10.3  Financing and Payment Capacity.  Before commencement and thereafter upon reasonable grounds, Owner shall provide reasonable evidence that funds are available to satisfy Owner's open-ended T&M obligations. If evidence is not provided within a reasonable time, Contractor may suspend affected Work after notice and recover resulting cost and time.

10.4  Permits and Legal Authorizations.  Owner shall obtain easements, zoning approvals, entitlements, and legal authorizations assigned to Owner and shall cooperate with Contractor in obtaining permits and inspections assigned to Contractor.

10.5  Design Professionals and Separate Work.  Owner shall require its architects, engineers, consultants, occupants, and separate contractors to coordinate with Contractor, comply with the schedule and site rules, and maintain appropriate insurance. Owner is responsible for their acts and omissions and resulting cost or delay.

10.6  Right to Stop or Carry Out Work.  If Contractor fails to correct materially nonconforming Work after written notice and reasonable opportunity to cure, Owner may order affected Work stopped or may correct the default and deduct reasonable documented cost, subject to Contractor's right to dispute the action under Article 15.

# ARTICLE 11  |  PAYMENTS AND PROJECT COMPLETION

11.1  Deposit and Replenishment.  Owner shall pay the initial deposit or advance stated on the cover. Contractor may apply it to amounts due. If a replenishment requirement is stated below, Owner shall restore the deposit when invoiced. Any unapplied balance is credited on the final invoice.

| DEPOSIT AND STARTUP FUNDING | AGREED TERM |
| --- | --- |
| Initial deposit / advance | $____________ |
| Required replenishment balance or frequency |  |
| Mobilization or startup payment treatment |  |

11.2  Payment and Disputed Invoices.  Owner shall pay each invoice within the payment period stated below. To dispute an invoice, Owner shall, within the stated review period, give written notice identifying each disputed line item, the amount withheld, and the factual and contractual basis. Owner shall release and pay every portion not specifically disputed by the due date. Owner may withhold only the amount reasonably necessary to protect against documented billing error, defective Work, third-party claims, failure to pay lower tiers after receipt of payment, damage, or other material breach, and shall release the withheld amount when the basis is cured.

11.3  Retainage.  Retainage applies only if stated below and only to the Work or cost categories identified. It shall be reduced or released when the stated conditions are satisfied, subject to mandatory law.

| RETAINAGE | AGREED TERM |
| --- | --- |
| Retainage percentage | % ____________ |
| Cost categories subject to retainage |  |
| Reduction, early release, or special treatment |  |

11.4  Stored Materials.  Materials purchased for the Work are billable when delivered to the site or another approved location and properly identified, insured, protected, and supported by reasonable purchase records. Payment does not relieve Contractor of custody, protection, installation, or warranty responsibility.

11.5  Substantial Completion.  Substantial Completion occurs when the authorized Work or designated portion is sufficiently complete for Owner's intended use. Contractor shall submit a completion list and proposed allocation of security, utilities, maintenance, insurance, warranties, incomplete Work, and the deadline for completion.

11.6  Final Completion and Invoice.  After Final Completion or termination, Contractor shall deliver required closeout and a final invoice showing remaining T&M Cost, Fee / Profit, credits, retainage, deposit application, and amount due. Final Payment does not waive latent defects, warranty obligations, fraud, or claims previously reserved in writing.

| FINAL PAYMENT | AGREED TERM |
| --- | --- |
| Final invoice due after receipt |  |
| Required lien documentation |  |
| Additional Final Payment conditions |  |

11.7  Late Payment and Suspension.  An undisputed amount is late when it is not paid by the due date stated below. If the amount remains unpaid seven calendar days after Contractor gives written notice of nonpayment, Contractor may suspend all or affected Work without breach until all overdue undisputed amounts, accrued interest, and reasonable shutdown and remobilization costs are paid. Contractor is entitled to an adjustment for shutdown, delay, escalation, storage, demobilization, remobilization, and resulting time. Contractor shall also give any notice required by mandatory law.

11.8  Downstream Payment; Pay-if-Paid Acknowledgment.  Owner acknowledges that Contractor's subcontracts, purchase orders, consultant agreements, and other lower-tier agreements may expressly provide that Contractor's actual receipt of corresponding payment from Owner is a condition precedent to Contractor's obligation to pay the applicable subcontractor, supplier, consultant, or other lower-tier party for the same Work. To the fullest extent permitted by law and as stated in the applicable lower-tier agreement, except to the extent Owner's nonpayment results from Contractor's material breach concerning that same Work, Contractor has no duty to finance Owner's Project or advance its own funds for amounts Owner has not paid. Owner's failure to pay an undisputed amount when due may therefore cause corresponding lower-tier nonpayment, payment notices or liens, loss of labor or material availability, and suspension of all or affected Work after the notice required by the Contract or mandatory law. Except to the extent caused by Contractor's breach, Owner is responsible for the resulting cost and time, including shutdown, delay, escalation, storage, demobilization, remobilization, extended general conditions, lien-resolution cost, reasonable lower-tier claims, and applicable Contractor Fee / Profit. Contractor shall timely pay undisputed lower-tier amounts for which Contractor has received corresponding payment, as required by the applicable lower-tier agreement and mandatory law.

# ARTICLE 12  |  PROTECTION, INSURANCE, BONDS, AND INDEMNITY

12.1  Safety.  Contractor is responsible for its construction safety program and precautions and for protection of its workers, the Work, and adjacent property. Each Owner separate contractor remains responsible for its own safety and shall comply with site rules. Owner shall not direct unsafe Work or assume control of means and methods.

12.2  Damage and Emergencies.  Contractor shall promptly remedy damage caused by its negligent operations, subject to required property insurance. Owner is responsible for damage caused by Owner, occupants, design professionals, or separate contractors. In an emergency, Contractor may act to prevent threatened injury, damage, or loss and shall notify Owner promptly; resulting time and cost are compensable unless caused by Contractor's breach.

12.3  Insurance and Bonds.  Before the related exposure begins, the parties shall provide the following insurance, builder's risk, and bonds. Policy terms and endorsements control over certificates, and no certificate expands coverage. Premiums and project-specific insurance or bond cost are treated as stated in Article 3.

| Coverage | Each occurrence / claim | Aggregate | Endorsements / completed operations |
| --- | --- | --- | --- |
| Workers' compensation | Statutory |  |  |
| Employers' liability |  |  |  |
| Commercial general liability |  |  |  |
| Automobile liability |  |  |  |
| Umbrella / excess liability |  |  |  |
| Professional liability, if applicable |  |  |  |
| Contractor's pollution liability, if required |  |  |  |

| PROPERTY INSURANCE AND BONDS | AGREED TERM |
| --- | --- |
| Builder's risk purchaser and coverage |  |
| Deductible allocation and waiver of subrogation |  |
| Performance and payment bonds |  |
| Insurance and bond cost treatment |  |

12.4  Indemnification.  To the fullest extent permitted by law, Contractor shall indemnify Owner from third-party claims for bodily injury or tangible property damage, but only to the extent caused by the negligent acts or omissions of Contractor or those for whom it is responsible. Owner shall indemnify Contractor on the same basis for the negligent acts or omissions of Owner, its design professionals, or separate contractors. No party is required to indemnify another for the indemnitee's own negligence where prohibited by law.

# ARTICLE 13  |  CORRECTION AND WARRANTY

13.1  Uncovering.  If Work is covered contrary to a required inspection or written direction, Contractor shall uncover and replace it without additional compensation to the extent caused by Contractor's breach. If properly covered Work is directed to be uncovered and is conforming, the resulting time and cost are compensable; if nonconforming, Contractor bears the reasonable corrective cost.

13.2  Correction.  Contractor shall promptly correct rejected or nonconforming Work and shall bear resulting damage to other included Work to the extent caused by Contractor's failure to comply with the Contract Documents. Owner shall provide reasonable access for correction.

13.3  Correction Period.  For one year after Substantial Completion, or the longer period stated in a specific warranty, Contractor shall correct construction that does not conform to the Contract Documents after written notice. The obligation excludes ordinary wear, abuse, improper maintenance or operation, unauthorized modification, and failure caused by Owner-provided design, existing conditions, or materials or equipment not furnished by Contractor.

13.4  Construction Warranty.  Contractor warrants that materials and equipment furnished by Contractor will be new unless otherwise permitted, of good quality, and free from material defects not inherent in the specified quality, and that construction will conform to the Contract Documents. Contractor does not warrant a particular total cost, schedule outcome, or adequacy of Owner-provided design.

13.5  Acceptance of Nonconforming Work.  Owner may accept nonconforming Work by written agreement stating an appropriate billing credit and any effect on warranty, operation, maintenance, or future replacement.

# ARTICLE 14  |  SUSPENSION AND TERMINATION

14.1  Owner Suspension.  Owner may suspend all or part of the Work by written notice. Contractor shall protect the Work as directed and is entitled to payment for Work performed, commitments, protection, delay, escalation, storage, demobilization, remobilization, extended supervision, and schedule effect unless the suspension results from Contractor's uncured material breach.

14.2  Contractor Suspension or Termination.  Contractor may suspend or terminate for prolonged stoppage beyond its control, nonpayment, failure to provide required funding evidence or insurance, denial of access, unsafe conditions outside its control, or other material Owner breach, after the notice and cure periods stated below or required by law.

14.3  Owner Termination for Cause.  Owner may terminate for Contractor's material breach after written notice describing the default and reasonable opportunity to cure. Owner may take possession of paid-for materials and accept contingent assignments. Contractor remains entitled to payment for properly performed Work, subject to Owner's established offset for completion and damages.

14.4  Owner Termination for Convenience.  Owner may terminate without cause by written notice. Contractor shall stop as directed, protect the Work, terminate commitments where commercially reasonable, and deliver Project records for which Owner has paid. As a condition of termination, Owner shall pay: all outstanding invoices and all T&M Cost and Contractor Fee / Profit accrued through the effective date; materials and equipment procured, fabricated, stored, ordered, or subject to noncancelable commitment; lower-tier, cancellation, restocking, protection, storage, demobilization, and closeout cost; and Contractor Fee / Profit on the remaining authorized Work. Fee / Profit on remaining Work is calculated by applying the agreed percentage to Contractor's reasonable documented estimate of the T&M Cost required to complete the then-authorized scope. That estimate is used only to calculate the termination payment and is not a representation, warranty, or cap on final Project cost. Title to paid-for materials transfers only after receipt of the termination payment.

| SUSPENSION AND TERMINATION TERMS | AGREED TERM |
| --- | --- |
| Nonpayment notice and cure period | 7 calendar days after written notice of an overdue undisputed amount |
| Other material-breach notice and cure period |  |
| Termination-for-convenience fee or calculation | All accrued and committed cost, plus Fee / Profit on remaining authorized Work under Section 14.4 |

# ARTICLE 15  |  CLAIMS, DISPUTES, AND MISCELLANEOUS PROVISIONS

15.1  Claims and Continued Performance.  A Claim is a written demand seeking payment, time, interpretation, or other relief. The claimant shall provide prompt notice describing the event, known facts, requested relief, and available support. Pending resolution, Contractor shall continue undisputed Work and Owner shall pay undisputed amounts unless the Contract has been properly suspended or terminated or continued performance would be unsafe or unlawful.

15.2  Resolution Process.  Project representatives shall first attempt resolution. If unsuccessful, an executive of each party with settlement authority shall meet promptly. Unresolved Claims shall proceed to mediation and then to the binding method selected in Article 1. Either party may preserve a lien, bond, limitations, emergency, or provisional remedy without waiving mediation.

15.3  Consequential Damages.  To the fullest extent permitted by law, Owner and Contractor waive consequential, indirect, incidental, exemplary, and punitive damages arising from the Project, including loss of use, financing, business, and reputation. The waiver does not apply to fraud, willful misconduct, covered third-party indemnity, or the direct termination payment required by Section 14.4, including Contractor Fee / Profit on remaining authorized Work.

15.4  Governing Law.  The Contract is governed by the law of the Project location unless another law is stated below, subject to mandatory law that cannot be varied.

| LEGAL TERM | AGREED ELECTION |
| --- | --- |
| Governing law |  |
| Venue |  |

15.5  Notices.  Formal notices shall be delivered to the addresses and emails below by personal delivery, nationally recognized overnight carrier, certified mail, or email with confirmed transmission, subject to any method required by law. Routine Project communication may use the agreed electronic platform.

| Party | Recipient | Email | Delivery address |
| --- | --- | --- | --- |
| Owner |  |  |  |
| Contractor |  |  | Mefford Contracting, LLC, 1585 Mercer Road, Suite 110, Lexington, KY 40511 |

15.6  Assignment.  Neither party may assign the Contract without the other's written consent, not unreasonably withheld, except Owner may assign to a Project lender or successor that assumes Owner's obligations and Contractor may assign receivables to a lender. No assignment releases the assigning party without written consent.

15.7  Confidential Information.  Each party shall protect nonpublic business, pricing, security, personal, and technical information using reasonable care and shall use it only for the Project. The duty does not apply to information lawfully public, independently developed, already known without restriction, or required to be disclosed by law.

15.8  Rights, Remedies, and Severability.  Rights and remedies are cumulative unless the Contract expressly states otherwise. A waiver is effective only in writing and only for the stated instance. If a provision is unenforceable, it shall be limited or severed to the minimum extent necessary and the remaining provisions continue in effect.

15.9  Electronic Signatures and Counterparts.  This Agreement and later Modifications may be executed in counterparts and by legally valid electronic signature. Each signed counterpart is deemed an original and together they form one instrument.

# ARTICLE 16  |  CONTRACT DOCUMENTS AND EXECUTION

16.1  Included Documents.  This Agreement consists of the documents listed below. A proposal, estimate, cost report, drawing, specification, schedule, planning statement, Work Authorization, or attachment is not part of the Contract unless specifically identified by title, date, and revision.

| Document | Title / identifier | Date / revision | Purpose |
| --- | --- | --- | --- |
| This Agreement | MC-OWN-TM-001 REV. 1.2 |  | Authorization for open-ended time-and-materials construction |

16.2  Order of Precedence.  A later signed Modification controls over earlier documents. Mandatory law controls next, followed by this Agreement and specifically listed Work documents. A specific requirement controls over a general requirement. Lower-tier terms do not modify Owner's or Contractor's rights unless expressly incorporated.

16.3  Entire Agreement.  The Contract Documents are the complete agreement concerning the Work. No prior or contemporaneous proposal, estimate, planning statement, discussion, representation, or course of dealing modifies the Contract unless specifically incorporated in Article 16.1.

# SIGNATURES

| EXECUTION INFORMATION | AGREED VALUE |
| --- | --- |
| Owner legal name |  |
| Project |  |
| Agreement effective date |  |

The parties execute this Agreement through their authorized representatives. This execution authorizes Contractor to begin and continue the Work on a time-and-materials basis without a fixed total Contract Sum, subject to Owner's written stop direction and authorized Modifications.

| OWNER | MEFFORD CONTRACTING, LLC |
| --- | --- |
| Legal name: __________________________ | By: __________________________________ |
| By: __________________________________ | Printed name: _________________________ |
| Printed name: _________________________ | Title: _________________________________ |
| Title: _________________________________ | Date: __________________________________ |
| Date: __________________________________ |  |